## Timing Sheet_MainMenu
Task | Date | Baseline estimate | Start | End | Interruptions | Measured time (hours) | Percentage | Adjusted estimate
Research Main MenuUI Layouts | 2021-02-16 | 0:15 | 13:00 | 13:15 | 0:00 | 0.25 | 2400% | 0.25
Look at main elements of a Main Menu screen | 2021-02-16 | 0:10 | 13:15 | 13:30 | 0:00 | 0.25 | 3600% | 0.25
Create button designs | 2021-02-16 | 0:25 | 13:30 | 14:00 | 0:00 | 0.5 | 2880% | 0.5
Place the Buttons on Unity and Lay them out in correct positions | 2021-02-16 | 0:10 | 14:00 | 14:25 | 0:05 | 0.33333 | 4800% | 0.33333
Begin Coding for Start and Quit Buttons | 2021-02-16 | 0:45 | 14:25 | 15:00 | 0:00 | 0.58333 | 1867% | 0.58333
Implament the Settings button design | 2021-02-16 | 0:15 | 15:00 | 15:05 | 0:00 | 0.083333 | 800% | 0.083333
Code and Functions for Options button | 2021-02-16 | 0:45 | 15:05 | 15:45 | 0:00 | 0.66667 | 2133% | 0.66667

## Timing Sheet_Character Movement
Task | Date | Baseline estimate | Start | End | Interruptions | Measured time (hours) | Percentage | Adjusted estimate
Add in your Character to the scene and make sure it is clear which way is front of the character | 2021-02-23 | 0:05 | 13:00 | 13:15 | 0:00 | 0.25 | 7200% | 0.25
Install Cinemachine in the package manager | 2021-02-23 | 0:05 | 13:10 | 13:30 | 0:00 | 0.33333 | 9600% | 0.33333
Set Up the camera for unity so it is in correct position and is funcitoning correctly | 2021-02-23 | 0:15 | 13:15 | 14:00 | 0:00 | 0.75 | 7200% | 0.75
Begin Creating the Scipt for the character | 2021-02-23 | 1:00 | 13:25 | 14:25 | 0:00 | 1 | 2400% | 1
Add in the Cinemachine Collider, and configure the tags to have a Ground tag | 2021-02-23 | 0:10 | 14:10 | 15:00 | 0:00 | 0.83333 | 12000% | 0.83333

## Timing Sheet_PlanetOrbit
Task | Date | Baseline estimate | Start | End | Interruptions | Measured time (hours) | Percentage | Adjusted estimate
Add a Sphere and Player Shape and scale the character slightly smaller than the planet to be above the planet | 2021-03-02 | 0:15 | 13:00 | 13:10 | 0:00 | 0.53819 | 5167% | 0.53819
Codeing the planet, so that it has gravity for something that has player gravity on it to stick together | 2021-03-02 | 0:55 | 13:10 | 13:55 | 0:00 | 0.54167 | 1418% | 0.54167
player script for movement | 2021-03-02 | 1:00 | 14:05 | 15:00 | 0:10 | 0.58333 | 1400% | 0.58333
Code So Player Gravity Attracts to planet | 2021-03-02 | 1:00 | 15:00 | 15:45 | 0:00 | 0.61458 | 1475% | 0.61458

## Timing Sheet_NPC Interaction
Task | Date | Baseline estimate | Start | End | Interruptions | Measured time (hours) | Percentage | Adjusted estimate
Create a background pane and a canvas with 2 buttons on them | 2021-03-09 | 0:05 | 13:00 | 13:10 | 0:00 | 0.16667 | 4800% | 0.16667
scripting the buttons to allow to place text in inspector | 2021-03-09 | 0:05 | 13:10 | 13:30 | 0:00 | 0.33333 | 9600% | 0.33333
Added in how what text I want to appear in the console | 2021-03-09 | 0:15 | 13:15 | 14:00 | 0:00 | 0.75 | 7200% | 0.75
Created a StartDialogue Code which made it so that when you press the button he starts the conversation while adding in a On Click Function | 2021-03-09 | 1:00 | 13:25 | 14:25 | 0:00 | 1 | 2400% | 1