## Sheet1
4 Unity packages | DATE | START | END | BREAK | HOURS | Estimated time (Hours) | Percentage | Ajusted estimate | DESCRIPTION
Unity package 1 | 2021-02-09 | 10:00 | 12:30 | 0:30 | 3 | 4 | 75% | 3 | Created AI script that moves towards objects with certain name
Unity package 1 | 2021-02-09 | 12:30 | 13:00 | 0:00 | 0.5 | 1 | 50% | 0.5 | Made a script for another object to follow the AI created above
Unity package 1 | 2021-02-11 | 15:00 | 16:20 | 0:20 | 1 | 1 | 100% | 1 | Made it so the AI moves to a random object instead of the next one in an array
Unity package 2 | 2021-02-16 | 9:00 | 11:10 | 0:40 | 2 | 0.5 | 400% | 2 | Created a UI button when clicked add score to an int
Unity package 2 | 2021-02-20 | 11:30 | 12:45 | 0:15 | 1 | 0.5 | 200% | 1 | Change the scale of the button when clicked
Unity package 2 | 2021-02-23 | 16:00 | 17:10 | 0:10 | 1 | 1 | 100% | 1 | Created a score system that shows on ui
Unity package 3 | 2021-02-23 |  | 12:30 | 0:00 | 1.5 | 1 | 150% | 1.5 | PauseMenu script
Unity package 3 |  | 15:00 | 15:30 | 0:00 | 0.5 | 1 | 50% | 0.5 | Added buttons to the pause menu - resume/ restart/ quit to main menu
Unity package 4 |  | 22:00 | 23:15 | 0:15 | 1 | 2 | 50% | 1 | Added Script that instatinated a ball on mouse click on mouse location
Unity package 4 |  | 23:30 | 0:40 | 0:10 | 1 | 0.5 | 200% | 1 | Added a score script to if the ball landed in the score zone
Unity package 4 |  | 23:30 | 0:40 | 0:10 | 1 | 0.5 | 200% | 1 | Added a negative score if it landed outside of the score zone
Unity package 4 |  | 23:30 | 0:40 | 0:10 | 1 | 1 | 100% | 1 | Added a ScoreUI to show of all points on a ui display
Small game | DATE | START | END | BREAK | HOURS | Estimated time (hours) | Percentage | Ajusted estimate | DESCRIPTION
|  | 12:00 | 13:00 | 0:00 | 1 | 1 | 100% | 1 | Created a pause menu /With buttons
|  | 10:00 | 13:00 | 0:00 | 3 | 4 | 75% | 3 | Created an object that goes to an object with name
|  | 10:00 | 12:00 | 0:15 | 1.75 | 2 | 87.5% | 1.75 | Created script that drops the objects with certain name for previous script
|  | 13:00 | 14:30 | 0:00 | 1.5 | 1 | 150% | 1.5 | Created a score script that takes score from other scripts
|  | 13:30 | 15:00 | 0:00 | 1.5 | 1 | 150% | 1.5 | Created ui to show of the score
|  | 13:30 | 15:00 | 0:30 | 1.5 | 0.5 | 300% | 1.5 | Created a script that ends the game when score reaches a certain point