## Sheet1
Task | Description of Task | Date | Baseline Estimate | Start | End | Interruptions | Percentage | Adjusted Estimate
Package 1:
Button Pressing Videos | Watch videos on clickable objects | 2021-03-09 | 0:30 | 13:10 | 13:45 | 0:00 | 116% | 0:35
MouseDown reading | Reading documentation on the variable | 2021-03-09 | 0:15 | 13:45 | 14:05 | 0:05 | 125% | 0:20
Door Open Script | Door Opening Position Script | 2021-03-09 | 0:15 | 14:10 | 14:20 | 0 | 66% | 0:10
Make Player Controller | Character controller | 2021-03-09 | 0:20 | 14:25 | 14:50 | 0:00 | 125% | 0:25
Door Close Script | Door Closing Position Script | 2021-03-09 | 0:15 | 14:55 | 15:10 | 0 | 100% | 0:15
Test Buttons | Test the scripts | 2021-03-09 | 0:10 | 15:10 | 15:25 | 0:05 | 150% | 0:15
Write up the documentation | Documentation for the components | 2021-03-09 | 0:15 | 15:25 | 15:40 | 0 | 100% | 0:15
Package 2:
Pickup Object 3D Videos | Watch videos on collision and objects | 2021-03-16 | 0:20 | 13:05 | 13:30 | 0 | 125% | 0:25
particle tutorials | Info on particle tutorials | 2021-03-16 | 0:25 | 13:30 | 13:55 | 0:00 | 100% | 0:25
set up unity scene | Set up with cubes and spheres | 2021-03-16 | 0:05 | 14:00 | 14:08 | 0:02 | 160% | 0:08
player controller | Make a character controller script | 2021-03-16 | 0:15 | 14:10 | 14:20 | 0 | 66% | 0:10
write pickup script | script for collision with player | 2021-03-16 | 0:15 | 14:25 | 14:45 | 0 | 133% | 0:20
write particle script | write script for particle after effect | 2021-03-16 | 0:30 | 14:45 | 15:15 | 0:00 | 100% | 0:30
Test collisions | Test the player and object triggers | 2021-03-16 | 0:05 | 15:15 | 15:20 | 0 | 100% | 0:05
Write up the documentation | Documentation for the components | 2021-03-16 | 0:20 | 15:20 | 15:40 | 0 | 100% | 0:20
Package 3:
Destroy Object documents | Read destroy object documents | 2021-03-23 | 0:10 | 13:15 | 13:25 | 0 | 100% | 0:10
Text output script documents | Text appear on trigger documents | 2021-03-23 | 0:25 | 13:35 | 14:00 | 0 | 100% | 0:25
set up scene | Set up the Unity Scene | 2021-03-23 | 0:05 | 14:00 | 14:07 | 0:00 | 140% | 0:07
player controller | Script a player controller | 2021-03-23 | 0:05 | 14:10 | 14:20 | 0 | 200% | 0:10
write line script | text appear on trigger script | 2021-03-23 | 0:35 | 14:25 | 15:05 | 0 | 116% | 0:40
destroy player script | write the script to destroy the player | 2021-03-23 | 0:05 | 15:05 | 15:10 | 0 | 100% | 0:05
Test finish line | Test that both scripts work | 2021-03-23 | 0:05 | 15:15 | 15:20 | 0:00 | 100% | 0:05
Write up the documentation | Documentation for the components | 2021-03-23 | 0:20 | 15:20 | 15:42 | 0:00 | 110% | 0:22
Package 4:
Set up little course | Set up Unity Scene with cubes | 2021-03-30 | 0:15 | 13:10 | 13:30 | 0:05 | 133% | 0:20
Research Checkpoints | Watch videos of checkpoints in Unity 3D | 2021-03-30 | 0:45 | 13:30 | 14:15 | 0:05 | 100% | 0:45
Read forums | Read documentation and forums | 2021-03-30 | 0:20 | 14:20 | 14:35 | 0:00 | 75% | 0:15
Script Writing | Writing hit detection script | 2021-03-30 | 0:15 | 14:40 | 14:55 | 0 | 100% | 0:15
Script Writing | Writing respawn script | 2021-03-30 | 0:30 | 15:00 | 15:30 | 0 | 100% | 0:30
Testing respawing | Testing checkpoints | 2021-03-30 | 0:05 | 15:30 | 15:40 | 0 | 150% | 0:10
Fix Inconsistent collision | Inconsistent Collision for player and cube | 2021-03-30 | 0:10 | 15:40 | 16:10 | 0 | 166% | 0:30
Write up the documentation | Documentation for the components | 2021-03-30 | 0:20 | 16:10 | 16:30 | 0 | 100% | 0:20
Project:
Set up Unity Scenes (5) | Set up 5 levels for the small project | 2021-04-06 | 0:15 | 13:10 | 13:30 | 0 | 133% | 0:20
Add Platforms | Platforms used in the levels | 2021-04-06 | 0:30 | 13:32 | 14:04 | 0 | 106% | 0:32
Add Packages to Level 1 | Add my packages to the first level | 2021-04-06 | 1:00 | 14:10 | 15:10 | 0 | 100% | 1:00
Changing Package Code | Adjusting Door Code | 2021-04-06 | 0:02 | 15:10 | 15:12 | 0 | 100% | 0:02
Writing Extra Scripts | Some extra scripts for the levels | 2021-04-13 | 0:30 | 13:00 | 13:34 | 0:02 | 112% | 0:34
Research Turret Videos | Turret Videos | 2021-04-13 | 0:25 | 13:40 | 14:00 | 0 | 80% | 0:20
Turret Coding | Writing Code for the Player and Turret | 2021-04-13 | 1:00 | 14:05 | 15:20 | 0:10 | 125% | 1:15
Add Turrets to Level 2 | Set up turrets to shoot in Level 2 | 2021-04-13 | 0:10 | 15:22 | 15:32 | 0 | 100% | 0:10
Add Packages to Level 2 | Add my packages to the second level | 2021-04-13 | 0:15 | 15:40 | 15:55 | 0 | 100% | 0:15
Create a First person controller | Create a player controller (first person) | 2021-04-20 | 0:40 | 13:00 | 13:50 | 0 | 125% | 0:50
Test First Two Levels | Testing levels to see if they work as intended | 2021-04-20 | 0:05 | 14:00 | 14:05 | 0 | 100% | 0:05
Add Canvas and text | Add canvas for coins and other text | 2021-04-20 | 0:10 | 14:10 | 14:15 | 0 | 50% | 0:05
Add packages to Level 3 | Add my packages to the third level | 2021-04-20 | 0:10 | 14:15 | 14:25 | 0 | 100% | 0:10
Add Packages to Level 4 | Add my packages to the fourth level | 2021-04-20 | 0:10 | 14:30 | 14:45 | 0:05 | 150% | 0:15
Animate platforms in Level 4 | Animate some moving platforms | 2021-04-20 | 0:30 | 14:45 | 15:23 | 0 | 121% | 0:38
Add Turrets to Level 3 | Set up turrets to shoot in Level 3 | 2021-04-20 | 0:10 | 15:25 | 15:40 | 0:05 | 150% | 0:15
Add Turrets to Level 4 | Set up turrets to shoot in Level 4 | 2021-04-20 | 0:10 | 15:40 | 15:50 | 0 | 100% | 0:10
Change platforms for level 5 | Change layout | 2021-04-27 | 0:30 | 13:10 | 13:50 | 0 | 133% | 0:40
Add new door height button | Change the height for the door button | 2021-04-27 | 0:05 | 14:00 | 14:05 | 0 | 100% | 0:05
Change turrets sight | Change the sight area for the turrets | 2021-04-27 | 0:10 | 14:05 | 14:15 | 0 | 100% | 0:10
Add Spawning collsion | Spawn and removal for objects | 2021-04-27 | 0:25 | 14:20 | 14:45 | 0 | 100% | 0:25
Set up checkpoint for middle platform | Checkpoint for the middle platform | 2021-04-27 | 0:30 | 14:45 | 15:15 | 0 | 100% | 0:30
Add Turrets to Level 5 | Set up turrets to shoot in Level 5 | 2021-04-27 | 0:15 | 15:15 | 15:40 | 0 | 166% | 0:25
Test all 5 Levels | Test all levels | 2021-04-27 | 0:20 | 15:40 | 16:00 | 0 | 100% | 0:20