## Sheet1
Task | Date | Baseline Estimate | Start | End | Interruptions | Measured time (Hours) | Percentage
Setting up project - double jump, adding rigidbody etc | 2021-02-16 | 0.05 | 11:30 | 11:35 |  |  | 1%
Writing code for double jump | 2021-02-16 | 1.5 | 11:45 | 13:17 |  | 1.37 | 0.91%
Setting up project - movement and camera follow | 2021-02-23 | 0.1 | 13:30 | 13:45 | 0.05 | 0.15 | 1.5%
Writing camera follow code | 2021-02-23 | 0.2 | 13:50 | 14:05 |  | 0.15 | 0.75%
Writing Player Movement code | 2021-02-23 | 0.4 | 14:02 | 14:46 |  | 0.44 | 1.1%
Setting project - pick up | 2021-03-02 | 0.05 | 13:10 | 13:13 |  | 0.03 | 0.6%
adding rigidbody to player and adding movement code | 2021-03-02 | 0.3 | 13:14 | 13:48 | 0.04 | 0.34 | 1.13%
fixing broken script | 2021-03-02 | 0.15 | 13:50 | 14:20 |  | 0.3 | 2%
Pick Up script | 2021-03-02 | 0.35 | 14:25 | 15:12 | 0.12 | 0.47 | 1.34%
Making scene, adding rigidbody, checking specfic boxes are ticked | 2021-03-09 | 0.2 | 13:10 | 13:25 |  | 0.15 | 0.75%
Adding player movement | 2021-03-09 | 0.05 | 13:25 | 13:30 |  | 0.05 | 1%
Writing triggerRespawn script | 2021-03-09 | 0.3 | 13:30 | 14:10 | 0.1 | 0.4 | 1.3%
Adding triggerRespawn script | 2021-03-09 | 0.05 | 14:10 | 14:21 | 0.06 | 0.11 | 2.2%
Setting up scene | 2021-03-23 | 0.15 | 13:20 | 13:40 | 0.05 | 0.2 | 1.3%
Adding tags to objects and adding rigidbody and freeze rotation to player | 2021-03-23 | 0.05 | 13:40 | 13:43 |  | 0.03 | 0.6%
Adding double jump, camera follow and movement | 2021-03-23 | 0.3 | 13:45 | 14:25 | 0.1 | 0.4 | 1.3%
Setting up project | 2021-04-05 | 0.05 | 10:50 | 10:57 | 0.02 | 0.07 | 1.4%
Adding all assets and code into unity | 2021-04-05 | 0.1 | 12:23 | 12:34 | 0.01 | 0.11 | 1.1%
adding rigidbody to player, adding tags to objects | 2021-04-08 | 0.15 | 10:02 | 10:24 | 0.12 | 0.22 | 1.46%
setting code to where it is meant to be and adjusting settings | 2021-04-08 | 0.35 | 10:30 | 11:10 | 0.1 | 0.4 | 1.14%
mapping out level | 2021-04-14 | 0.2 | 15:20 | 15:35 |  | 0.15 | 0.75%
0.05